## Updated Tasks
Task ID | Task Name | Bucket | Previous Status | Updated Status | Assessment | Assigned To | Start date | Due date | Completed Date | Completed Checklist Items | Checklist (updated) | Remaining / evidence to attach | Labels | Parent Task ID
s6C-ZlJ_EEmKKIxjtc9IQMkAHxjj | Set up the tenant database and sample tenants | Sprint 1 | Completed | Completed | Verified | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-01 | 2026-10-09 | 7/7 | [x] Create PostgreSQL database using Docker [x] Configure Row-Level Security policies [x] Create three sample tenants [x] Create restricted application database role [x] Enable pgvector and UUID extensions [x] Run tenant isolation tests [x] Create tenants, users, knowledge_base and audit_log tables |  | C4 Platform-Email
Tebj5Z6QvU-SkCkqfGl5_8kALvN6 | Set up the team GitHub repository | Sprint 1 | Completed | Completed | Export reported only | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-01 | 2026-10-08 | 2/5 | [x] Create Repository [ ] Add Collaborators [ ] Verify Team Repository Access [x] Create Branches [ ] Protect Main Branch | Attach collaborator-access and branch-protection screenshots. | Team
K0IRlzBiPESovq7UxQO9RMkAPHa4 | Meet the supervisor to approve scope and Finalize the Individual Report | Sprint 1 | Completed | Completed | Export reported only | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-09-14 | 2026-09-15 | 2026-10-09 | 0/3 | [ ] Create Individual Reports [ ] Discuss with the Supervisor [ ] Get Supervisor Signature | Attach signed report / meeting record (completed 14 Sep per export). | Team
dvN4Bp4-KkKQe7Aqo54-C8kAKMfB | Set up Planner and add Sprint 1 and 2 tasks | Sprint 1 | Completed | Completed | Verified | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-01 | 2026-10-09 | 4/4 | [x] Create Planner [x] Assign People [x] Create Sprints [x] Add Tasks |  | Team
509o6p7yikitvlPbyR7PJskAM4z6 | Create diary and AI-use log templates | Sprint 1 | Completed | Completed | Export reported only | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-10-01 | 2026-10-02 | 2026-10-20 | 0/4 | [ ] Each member fills in their first entry [ ] Create the weekly diary template [ ] Create the AI-use log template [ ] Upload both templates to the team SharePoint folder | Tick items once templates/SharePoint evidence is attached. | Team
CQQEW_of-0eHfsbhnzLXuMkAOfC6 | Agree and record key project decisions | Sprint 1 | Completed | Completed | Export reported only | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-10-01 | 2026-10-02 | 2026-10-10 | 0/6 | [ ] Agree on the multi-tenant approach [ ] Agree on GitHub branching, commit and PR review rules [ ] All members confirm the decisions [ ] Record the decisions in a decision log [ ] Agree on the tech stack and frameworks [ ] Hold a team decision meeting | Attach Decision_Log.xlsx and meeting minutes. | Team
bRMfwq5CIEK8RBSyaDHxU8kALbNy | Define API contracts and sample responses | Sprint 1 | Completed | Completed | Partial | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-10-02 | 2026-10-04 | 2026-10-20 | 5/11 | [x] Define the standard error format and status codes [x] Define request and response schemas [x] Define the auth and tenant ID headers [x] Add sample JSON responses for each endpoint [x] Document implemented C4 platform endpoints and integration limitations [ ] List the endpoints for each component [ ] Commit the contracts to GitHub [ ] Review the contracts with the team [ ] C3: I-04 lead-score contract + mock (team) [ ] C3: I-05 lead-recommendation contract + mock (team) [ ] C3 I-04 v1.1.0 + I-05 v1.1.0 with mocks (team) | C3 contract/mock files are owned by C3; attach commit evidence. | Team
2G80Ovxsb0a9o6MtQHEGA8kAF9IF | Review Sprint 1 progress and risks | Sprint 1 | Completed | Completed | Export reported only | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-10-04 | 2026-10-04 | 2026-10-10 | 0/5 | [ ] Record lessons learned [ ] Check the completion status of every Sprint 1 task [ ] Identify incomplete tasks and move them to Sprint 2 [ ] Confirm the Sprint 2 plan [ ] Update the risk register | Attach risk register / review minutes. | Team
L3DNfb9RQEu-NHNd75u1BckAEBcJ | Add authentication and secure tenant identification | Sprint 2 | Completed | Completed | Verified | SAAYINATH K it23304338 | 2026-10-05 | 2026-10-06 | 2026-10-10 | 8/8 | [x] Create JWT login endpoint [x] Test missing and invalid JWT [x] Implement protected user and tenant endpoints [x] Test valid and invalid credentials [x] Implement bcrypt password verification [x] Create JWT verification middleware [x] Restore identity through HTTP-only cookies and revoke sessions on logout [x] Reject forged tenant/role registration and cross-origin/CSRF mutations |  | C4 Platform-Email
d15ir2Ejp0y8X0EVS5BJm8kAJyOT | Add role-based access permissions | Sprint 2 | Completed | Completed | Verified | SAAYINATH K it23304338 | 2026-10-06 | 2026-10-07 | 2026-10-10 | 7/7 | [x] Implement authorize middleware [x] Protect admin-only route [x] Test all nine role-route combinations [x] Protect campaign management route [x] Protect campaign viewing route [x] Define agency_admin, marketer and viewer permissions [x] Apply live role changes and account deactivation to existing sessions |  | C4 Platform-Email
b1g6dPubUEqavE0O4L3aiskAJOrB | Connect agent services through the API gateway | Sprint 2 | In progress | In progress | Partial | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-08 |  | 3/11 | [x] Enforce roles and tenant context [x] Expose C4 workspace and email APIs with explicit disconnected statuses [x] Test C4 denied, unavailable-model and malformed-model responses [ ] Define shared agent request and response contract [ ] Connect Component 1 API endpoint [ ] Connect Component 2 API endpoint [ ] Connect Component 3 API endpoint [ ] Create mock agent for unavailable services [ ] Implement authenticated gateway proxy [ ] Configure internal service URLs and credentials [ ] Test successful, denied and unavailable-agent responses | C1/C2/C3 services and the gateway proxy are not yet implemented. | C4 Platform-Email
tWW3Lz5eikqqko1AQ6-PhckAAchW | Record API actions in audit logs | Sprint 2 | In progress | Completed | Verified | SAAYINATH K it23304338 | 2026-10-08 | 2026-10-09 | 2026-10-21 | 5/5 | [x] Record tenant, user, action and route [x] Record successful API access [x] Verify audit records in PostgreSQL [x] Create audit logging middleware [x] Record denied API access | Scope: routes using audit middleware (6 allowed + 3 denied verified). Auth failures and some CRUD routes not covered. | C4 Platform-Email
GUVHbCA7PkqbbEu18R3v7ckAM1L6 | Show each first key function to the supervisor | Sprint 2 | In progress | In progress | Partial | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-10-09 | 2026-10-09 |  | 1/7 | [x] Collect C4 overview, account, membership and mobile demo screenshots [ ] Each member prepares a demo of their first key function [ ] Prepare a short demo order or script [ ] Schedule the meeting with the supervisor [ ] Run the demos [ ] Record the supervisor's feedback [ ] Create follow-up tasks from the feedback | No supervisor demo record yet. | Team
CAUKFn_9p0eQoa1HyoThaMkABDY5 | Review Sprint 2 progress and GitHub contributions | Sprint 2 | Completed | Completed | Export reported only | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-10-09 | 2026-10-09 | 2026-10-14 | 0/5 | [ ] Check that PRs were reviewed and merged [ ] Move unfinished tasks and plan Sprint 3 [ ] Check commits per member on GitHub [ ] Update the risk register [ ] Review the Sprint 2 board status | Attach review evidence. | Team
YusHog_KNEi38rVn5hM3h8kAJ6Gl | Arrange the user-feedback session | Sprint 3 | In progress | In progress | Unverified | SAAYINATH K it23304338;JASINTHAN U it23154544;SHATHURSINI.J it23164062 | 2026-10-10 | 2026-10-10 |  | 0/4 | [ ] Agree the user-feedback goals and participant criteria [ ] Invite participants and record the confirmed session [ ] Prepare a runnable user journey and feedback questions [ ] Collect feedback and link findings and resulting tasks |  | C3 Lead-Intel
35EcnmgUHkmORnMzFR-ltskALTIN | Test tenant isolation and access permissions | Sprint 3 | Completed | Completed | Verified | SAAYINATH K it23304338 | 2026-10-11 | 2026-10-12 | 2026-10-10 | 6/6 | [x] Verify Tenant A can read its own records [x] Verify Tenant B can read its own records [x] Verify Tenant C can read its own records [x] Run RBAC tests for all roles [x] Verify unauthorized writes are blocked [x] Verify cross-tenant reads are blocked |  | C4 Platform-Email
k4qM_z973kysiXs_hnYkOMkAFABB | Generate a personalized three-step email sequence | Sprint 3 | In progress | In progress | Implemented; live test pending | SAAYINATH K it23304338 | 2026-10-11 | 2026-10-13 |  | 7/9 | [x] Define three-email sequence structure [x] Configure email agent and model [x] Prepare tenant-specific knowledge retrieval [x] Generate personalized subject lines and messages [x] Add safety and content checks [x] Save generated output and test evidence [x] Persist and reload manual email sequences without an AI dependency [ ] Test tenant-specific generation [ ] Pass a live tenant-context generation and persistence smoke test | Live Ollama generation returned HTTP 503 on 21 Oct; fine-tuned adapter not yet active. | C4 Platform-Email
TC0kO6inN0uNkshS4O9n7MkAOPSk | Connect all agents and test the complete workflow | Sprint 3 | Not started | In progress | Partial | SAAYINATH K it23304338 | 2026-10-12 | 2026-10-14 |  | 1/7 | [x] Run C4 registration, campaign, knowledge and saved-sequence workflow against PostgreSQL [ ] Connect Component 1 strategy service [ ] Connect Component 2 content service [ ] Connect Component 3 lead-intelligence service [ ] Verify identity/context handoffs between all four components [ ] Run complete multi-agent success, denial and failure scenarios [ ] Capture a complete integrated workflow trace and output evidence |  | C4 Platform-Email
NXPTfCPyvEq8vKZq-1PzMMkAB6ym | Check email privacy, consent, facts and tone | Sprint 3 | Not started | In progress | Partial | SAAYINATH K it23304338 | 2026-10-13 | 2026-10-14 |  | 4/8 | [x] Reject detected email/phone PII [x] Require unsubscribe wording on saved drafts [x] Reject spam phrases and excessive capitals [x] Measure offline offer/fact grounding on generated responses [ ] Enforce runtime grounding against tenant facts before saving [ ] Enforce the 150-word body limit in the save validator [ ] Verify recipient consent and process real opt-outs before delivery [ ] Review factual relevance and tone manually on an independent test set | Audit: unsupported 90% offer and 165-word body were accepted. | C4 Platform-Email
A46wNzBeX02RvIyc_ZhTCckADxwD | Review the 50% checkpoint with the supervisor | Sprint 3 | Not started | Not started | Unverified | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-10-14 | 2026-10-14 |  | 0/4 | [ ] Prepare individual progress, results and known limitations [ ] Arrange and conduct the 50% supervisor checkpoint [ ] Record supervisor feedback and approval [ ] Assign and track follow-up actions |  | Team
6cEFQK5jl0Cg9BgNbRp55ckAM_50 | Compare personalized emails with generic AI emails | Sprint 4 | Not started | In progress | Partial | SAAYINATH K it23304338 | 2026-10-15 | 2026-10-17 |  | 3/7 | [x] Use identical held-out validation prompts for base and fine-tuned models [x] Save per-response checks, latency, comparison table and training loss [x] Recalculate all-checks pass rates: base 6/25, fine-tuned 19/25 [ ] Compare the same briefs with and without personalization/context [ ] Evaluate all 171 validation prompts and an untouched test set [ ] Use a blinded human rubric (relevance, factuality, tone, personalization) [ ] Report uncertainty and grounding regression; no CTR claims |  | C4 Platform-Email
3aMfr5fB2kmDcv995Gn_u8kAGu0i | Add sequence timing, consent and suppression checks | Sprint 4 | Not started | In progress | Partial | SAAYINATH K it23304338 | 2026-10-15 | 2026-10-16 |  | 2/7 | [x] Validate three emails at offsets 0, 3 and 7 days [x] Require unsubscribe wording before saving [ ] Store recipient consent and auditable consent changes [ ] Maintain tenant-scoped suppression/unsubscribe records [ ] Check consent and suppression at the delivery boundary [ ] Implement scheduler (timezone, cancellation, retries, no duplicates) [ ] Test opt-out processing before subsequent steps |  | C4 Platform-Email
ng9K8ZXRykm5SWUSkhQJxckAIl44 | Add monitoring, traces and alerts | Sprint 4 | Not started | In progress | Partial | SAAYINATH K it23304338 | 2026-10-16 | 2026-10-18 |  | 3/7 | [x] Expose health, database latency and model availability [x] Persist and display workspace activity [x] Show disconnected delivery and agent services explicitly [ ] Add request/correlation IDs and traces [ ] Collect retained latency/error/throughput metrics [ ] Configure alert rules and notification delivery [ ] Trigger a failure and capture alert and trace evidence |  | C4 Platform-Email
oJdPS1cdFkK0oZ8vBSPr4MkACVWd | Build the engagement model and experiment store | Sprint 4 | Not started | Not started | Not implemented | SAAYINATH K it23304338 | 2026-10-16 | 2026-10-19 |  | 0/6 | [ ] Define genuine engagement labels [ ] Build leakage-controlled train/validation/test splits [ ] Train and evaluate an engagement predictor against a baseline [ ] Store tenant-scoped experiment variants and assignments [ ] Persist delivery/open/click events with deduplication [ ] Expose prediction/experiment APIs and test isolation |  | C4 Platform-Email
gq8so08bZECDFmScnMsw-ckAKti3 | Deploy the system and test performance | Sprint 4 | Not started | In progress | Partial | SAAYINATH K it23304338 | 2026-10-17 | 2026-10-19 |  | 4/7 | [x] Provide a Compose stack for frontend, gateway, database and migrations [x] Build the frontend and verify Nginx/gateway reachability [x] Verify fresh and repeated migrations [x] Run and save a local health load test (5 VUs/30 s, p95 390 ms, 0 failures) [ ] Pass live AI generation under realistic concurrency [ ] Test authenticated workflows and connected agents under load [ ] Record target-environment deployment and full-workflow performance |  | C4 Platform-Email
TV31rvZfMES0EYG9QHzpLskAOqsB | Test the full workflow and isolation across three tenants | Sprint 4 | Not started | In progress | Partial | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-10-17 | 2026-10-18 |  | 4/7 | [x] Verify own-record reads for all three sample tenants [x] Reject cross-tenant reads and inserts in three isolated workspaces [x] Verify campaign/knowledge/sequence ownership and stale-write rejection [x] Run the C4 browser journey [ ] Complete live AI generation for each tenant [ ] Connect and verify the C1-C4 workflow across three tenants [ ] Capture multi-agent workflow and isolation evidence |  | Team
gElqHoOhHEeeQD0cdwKmyMkAL141 | Prepare each member’s PP1 slides | Sprint 4 | Not started | Not started | Unverified | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-10-17 | 2026-10-19 |  | 0/4 | [ ] Prepare C4 problem, architecture and contribution slides [ ] Include measured evaluation results and limitations [ ] Add screenshots, demo sequence and remaining work [ ] Review and combine each member's PP1 slides |  | Team
Q-ddELlELU2toTK8qtU_CckAO1Oz | Prepare each member’s evidence folder | Sprint 4 | Not started | In progress | Partial | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-10-18 | 2026-10-19 |  | 2/4 | [x] Create a C4 evidence index (source, tests, screenshots, model results) [x] Retain successes, failures and unverified claims in the task audit [ ] Collect and review the other three members' evidence [ ] Publish the team evidence folder and record its location |  | Team
ILbFBYC4Y0SXQp-mKqnfoMkAOT46 | Run a timed rehearsal and practise Q&A | Sprint 4 | Not started | Not started | Unverified | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-10-19 | 2026-10-19 |  | 0/4 | [ ] Agree presentation/demo order and time budget [ ] Run and time the full team rehearsal [ ] Practise individual Q&A and record weak areas [ ] Record feedback and assign corrective tasks |  | Team
0ZVT67QIWk-91Ea1EJ8NqskALWXL | Rehearse the presentation and demo with the supervisor | Sprint 5 | Not started | Not started | Unverified | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-10-20 | 2026-10-20 |  | 0/3 | [ ] Schedule the supervisor rehearsal [ ] Rehearse the presentation and live demo [ ] Capture supervisor feedback and actions |  | Team
lPSAySqwKk-L1aPo-MJSYckAJmri | Fix all rehearsal feedback items | Sprint 5 | Not started | Not started | Unverified | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-10-20 | 2026-10-21 |  | 0/3 | [ ] Collect the rehearsal feedback register [ ] Assign and implement each correction [ ] Retest affected behaviour and record acceptance |  | Team
wWEaSgOMrECdkylZWwcNZskAEP5Q | Practise individual questions and explanations | Sprint 5 | Not started | Not started | Unverified | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-10-20 | 2026-10-21 |  | 0/3 | [ ] Explain tenancy, RLS, session auth, roles and ownership [ ] Explain QLoRA, dataset split, evaluation and grounding limits [ ] Practise individual questions and record practice |  | Team
WznWPEwGh0mf20UgYu20uMkANBrk | Freeze the code and test setup on a clean machine | Sprint 5 | Not started | In progress | Partial | SAAYINATH K it23304338 | 2026-10-21 | 2026-10-21 |  | 2/6 | [x] Run production build and unit/integration/browser checks [x] Verify fresh-database setup and repeated migrations [ ] Resolve and commit staged/unstaged changes [ ] Create and record the release/freeze commit or tag [ ] Clone and validate startup on a separate clean machine [ ] Verify AI/runtime dependencies and model setup on clean machine |  | C4 Platform-Email
oQ8dzx9J8UiOPzofV54RE8kAAKML | Finalize diaries, AI logs and PP1 submission evidence | Sprint 5 | Not started | In progress | Partial | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | 2026-10-21 | 2026-10-22 |  | 1/5 | [x] Package C4 source references, tests, screenshots and fine-tuning evidence [ ] Complete each member's diary and AI-use log [ ] Attach approved reports, final slides and supervisor evidence [ ] Check links and upload the final submission [ ] Record submission confirmation and final review | Diary in progress (supervisor signature pending). | Team
-C0Kc5Jh7kWzxY9qKakYI8kAIf9m | Add OAuth, webhooks, sync and recovery after PP1 | Backlog | Not started | In progress | Partial | SAAYINATH K it23304338 |  |  |  | 2/6 | [x] Implement Google ID-token verification, nonce challenges and explicit linking [x] Test provider failures, replay, email mismatch and unverified identities [ ] Complete a real Google account sign-in/link acceptance test [ ] Implement external-service OAuth grants and refresh [ ] Add authenticated, replay-safe, tenant-routed webhooks [ ] Implement synchronization, retries, recovery and reconciliation |  | C4 Platform-Email
NsSUAVg4VEChXYGsDLToDskAHv8Z | Optional: add tenant opt-in settings and API | Backlog | Not started | Not started | Not implemented | SAAYINATH K it23304338 |  |  |  | 0/5 | [ ] Define opt-in purposes, defaults and permission rules [ ] Persist tenant-scoped settings and changes [ ] Add authenticated settings APIs and admin UI [ ] Enforce opt-in decisions in integrations and delivery [ ] Test authorization, isolation and opt-in/opt-out transitions |  | C4 Platform-Email
NEW-C4-01 (new) | Build the responsive authenticated C4 workspace interface | Sprint 3 | — | Completed | Verified | SAAYINATH K it23304338 |  |  |  | 4/4 | [x] Overview, campaigns, email builder, knowledge, integrations, team, monitoring and settings pages [x] Route/action permissions from real session state [x] Light/dark theme and motion preferences [x] Layouts validated at 320, 390 and 768 px | Proposed new task — create in Planner (no Planner ID yet). | C4 Platform-Email | k4qM_z973kysiXs_hnYkOMkAFABB
NEW-C4-02 (new) | Implement self-service account registration and database-backed sessions | Sprint 2 | — | Completed | Verified | SAAYINATH K it23304338 |  |  |  | 4/4 | [x] Server-assigned admin + new workspace on registration [x] Password validation; reject client-chosen role/tenant [x] HTTP-only cookie sessions with CSRF/origin checks [x] Persist profile changes; revoke sessions on logout/deactivation | Proposed new task — create in Planner (no Planner ID yet). | C4 Platform-Email | L3DNfb9RQEu-NHNd75u1BckAEBcJ
NEW-C4-03 (new) | Implement Google identity verification and account linking | Backlog | — | Completed | Verified | SAAYINATH K it23304338 |  |  |  | 4/4 | [x] Google challenge and ID-token handlers [x] Single-use nonce, verified email, audience checks [x] Explicit (not email-only) account linking [x] Failure, replay, registration and linking tests | Proposed new task — create in Planner (no Planner ID yet). | C4 Platform-Email | -C0Kc5Jh7kWzxY9qKakYI8kAIf9m
NEW-C4-04 (new) | Add workspace invitations and live team membership controls | Sprint 2 | — | Completed | Verified | SAAYINATH K it23304338 |  |  |  | 4/4 | [x] Single-use expiring invitations bound to email/workspace/role [x] Accept invites without tenant/role substitution [x] Role changes and deactivation with live refresh [x] Protect self-role change and last active admin | Proposed new task — create in Planner (no Planner ID yet). | C4 Platform-Email | d15ir2Ejp0y8X0EVS5BJm8kAJyOT
NEW-C4-05 (new) | Persist campaign drafts, ownership and versioned changes | Sprint 3 | — | Completed | Verified | SAAYINATH K it23304338 |  |  |  | 4/4 | [x] Tenant-scoped campaign drafts with archive/restore [x] Reject foreign-workspace updates and stale versions [x] Keep delivery metrics unavailable until real events [x] Database persistence and cross-tab refresh verified | Proposed new task — create in Planner (no Planner ID yet). | C4 Platform-Email | TC0kO6inN0uNkshS4O9n7MkAOPSk
NEW-C4-06 (new) | Build the persistent manual email-sequence editor and library | Sprint 3 | — | Completed | Verified | SAAYINATH K it23304338 |  |  |  | 4/4 | [x] Create, edit, reopen, delete three-email drafts [x] Structure, guardrail, source-ownership and version checks [x] Saved work survives reload and new login [x] Viewers and foreign tenants denied | Proposed new task — create in Planner (no Planner ID yet). | C4 Platform-Email | k4qM_z973kysiXs_hnYkOMkAFABB
NEW-C4-07 (new) | Build the tenant knowledge library and generation source controls | Sprint 3 | — | Completed | Verified | SAAYINATH K it23304338 |  |  |  | 4/4 | [x] Admin add/remove workspace knowledge text [x] Text upload and source-selection UI [x] Retrieve only own tenant's selected/recent text [x] Reject foreign source IDs before model call | Proposed new task — create in Planner (no Planner ID yet). | C4 Platform-Email | k4qM_z973kysiXs_hnYkOMkAFABB
NEW-C4-08 (new) | Add workspace activity, database totals and automatic refresh | Sprint 4 | — | Completed | Verified | SAAYINATH K it23304338 |  |  |  | 4/4 | [x] Activity committed with campaign/knowledge/sequence changes [x] Database totals and UTC daily aggregates [x] 5 s workspace refresh, 15 s service-status refresh [x] Cross-tab updates and reset on tenant/role change | Proposed new task — create in Planner (no Planner ID yet). | C4 Platform-Email | ng9K8ZXRykm5SWUSkhQJxckAIl44
NEW-C4-09 (new) | Containerize C4 and verify repeatable database migrations | Sprint 4 | — | Completed | Verified | SAAYINATH K it23304338 |  |  |  | 4/4 | [x] React/Nginx, gateway and pgvector PostgreSQL in Compose [x] Ordered startup, loopback ports, volumes, healthchecks [x] Migration checksums; restricted-role forced RLS check [x] Fresh and repeated migration tests pass | Proposed new task — create in Planner (no Planner ID yet). | C4 Platform-Email | gq8so08bZECDFmScnMsw-ckAKti3
NEW-C4-10 (new) | Verify fine-tuning examples and the application prompt contract | Sprint 4 | — | Completed | Verified | SAAYINATH K it23304338 |  |  |  | 4/4 | [x] 715 training and 171 validation sequences [x] Reference answers pass application guardrails [x] Runtime prompt reconstruction matches [x] 5 validation products with no training overlap | Proposed new task — create in Planner (no Planner ID yet). | C4 Platform-Email | k4qM_z973kysiXs_hnYkOMkAFABB
NEW-C4-11 (new) | Train and retain the Mistral 7B QLoRA email adapter | Sprint 4 | — | Completed | Verified | SAAYINATH K it23304338 |  |  |  | 4/4 | [x] Two-epoch QLoRA notebook and training log [x] LoRA adapter and tokenizer artifacts saved [x] 448 tensor offsets validated; checksum recorded [x] Loss recorded: best val 0.8709 (step 40), final 0.9924 | Proposed new task — create in Planner (no Planner ID yet). | C4 Platform-Email | k4qM_z973kysiXs_hnYkOMkAFABB
NEW-C4-12 (new) | Evaluate base and fine-tuned email generation on held-out prompts | Sprint 4 | — | Completed | Verified | SAAYINATH K it23304338 |  |  |  | 4/4 | [x] Per-response results for 25 validation prompts [x] JSON/sequence/unsubscribe/grounding/offer/length/guardrail metrics [x] All-check pass: base 24% vs fine-tuned 76% [x] Grounding regression 92% -> 76% recorded | Proposed new task — create in Planner (no Planner ID yet). | C4 Platform-Email | 6cEFQK5jl0Cg9BgNbRp55ckAM_50
NEW-C4-13 (new) | Implement safe lead-name and campaign-link template rendering | Sprint 4 | — | Completed | Verified | SAAYINATH K it23304338 |  |  |  | 4/4 | [x] Keep first_name/cta_link tags in stored sequences [x] Render a copy with real lead/link values [x] Reject missing values, header injection, unsafe URLs [x] Handle $ in names safely | Proposed new task — create in Planner (no Planner ID yet). | C4 Platform-Email | k4qM_z973kysiXs_hnYkOMkAFABB
NEW-C4-14 (new) | Automate isolated account/platform and responsive browser regression checks | Sprint 4 | — | Completed | Verified | SAAYINATH K it23304338 |  |  |  | 4/4 | [x] 42 database-backed integration tests pass [x] 12 frontend/template unit tests pass [x] Browser journey with screenshots [x] 9 RBAC combos, 3-tenant isolation, audit persistence | Proposed new task — create in Planner (no Planner ID yet). | C4 Platform-Email | TV31rvZfMES0EYG9QHzpLskAOqsB
NEW-C4-15 (new) | Register and activate the fine-tuned Ollama model | Sprint 5 | — | In progress | Partial | SAAYINATH K it23304338 |  |  |  | 1/5 | [x] Provide adapter, tokenizer and Ollama Modelfile [ ] Verify adapter compatibility with the Ollama base version [ ] Create c4-email-ft and confirm in installed model list [ ] Point gateway at fine-tuned model and restart [ ] Pass tenant-context generation, guardrails and persistence with it | Fine-tuned model not yet active; base mistral:7b-instruct is running. | C4 Platform-Email | k4qM_z973kysiXs_hnYkOMkAFABB

## Summary
Status | Previous (export) | Updated
Completed | 12 | 27
In progress | 5 | 16
Not started | 19 | 8
Total | 36 | 51
Note: 'Updated' includes 15 proposed new C4 tasks (rows marked '(new)'); 'Previous' counts only the 36 original tasks. Update date: 22 Oct 2026.

## Consolidated Data
Task ID | Task Name | Bucket | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
s6C-ZlJ_EEmKKIxjtc9IQMkAHxjj | Set up the tenant database and sample tenants | Sprint 1 | Completed | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-01 | 2026-10-01 | false | 2026-10-09 | SAAYINATH K it23304338 | 7/7 | Create PostgreSQL database using Docker;Configure Row-Level Security policies;Create three sample tenants;Create restricted application database role;Enable pgvector and UUID extensions;Run tenant isolation tests;Create tenants, users, knowledge_base and audit_log tables | C4 Platform-Email | PostgreSQL database initialized with pgvector, three sample tenants, tenant-aware tables and RLS policies. Restricted application role configured. Initial tenant isolation tests passed. Development security hardening remains necessary before production deployment.
Tebj5Z6QvU-SkCkqfGl5_8kALvN6 | Set up the team GitHub repository | Sprint 1 | Completed | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-01 | 2026-10-01 | false | 2026-10-08 | SAAYINATH K it23304338 | 5/5 | Create Repository;Add Collabrators;Verify Team Repository Access;Create Branches;Protect Main Branch | Team
K0IRlzBiPESovq7UxQO9RMkAPHa4 | Meet the supervisor to approve scope and Finalize the Individual Report | Sprint 1 | Completed | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-07 | 2026-09-15 | 2026-09-14 | false | 2026-10-09 | SAAYINATH K it23304338 | 3/3 | Create Individual Reports;Discuss with the Supervisor;Get Supervisor Signature | Team | Completed on 14th September
dvN4Bp4-KkKQe7Aqo54-C8kAKMfB | Set up Planner and add Sprint 1 and 2 tasks | Sprint 1 | Completed | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-01 | 2026-10-01 | false | 2026-10-09 | SAAYINATH K it23304338 | 4/4 | Create Planner;Assign People;Create Sprints;Add Tasks | Team
509o6p7yikitvlPbyR7PJskAM4z6 | Create diary and AI-use log templates | Sprint 1 | Completed | Important | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-02 | 2026-10-01 | false | 2026-10-20 | SHATHURSINI.J it23164062 | 0/4 | Each member fills in their first entry;Create the weekly diary template (date, attendees, work done, issues, next steps);Create the AI-use log template (date, tool, purpose, prompt summary, how the output was used, how it;Upload both templates to the team SharePoint folder | Team | Evidence Diary_Template.docx AI_Use_Log_Template.xlsx SharePoint_Templates_Folder.png
CQQEW_of-0eHfsbhnzLXuMkAOfC6 | Agree and record key project decisions | Sprint 1 | Completed | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-02 | 2026-10-01 | false | 2026-10-10 | SAAYINATH K it23304338 | 6/6 | Agree on the multi-tenant approach (tenant identification, data isolation);Agree on GitHub branching, commit and PR review rules;All members confirm the decisions;Record the decisions in a decision log;Agree on the tech stack and frameworks;Hold a team decision meeting | Team | Evidence Decision_Log.xlsx (decision, reason, date, agreed by) Decision_Meeting_Minutes.docx Teams_Meeting_Attendance.png
bRMfwq5CIEK8RBSyaDHxU8kALbNy | Define API contracts and sample responses | Sprint 1 | Completed | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-04 | 2026-10-02 | false | 2026-10-20 | SHATHURSINI.J it23164062 | 4/11 | C3: I-05 contract + mock;Define the standard error format and status codes;Define request and response schemas;List the endpoints for each component;C3: I-05 lead-recommendation contract + mock (commit 89781CD;Define the auth and tenant ID headers;Commit the contracts to GitHub;C3 I-04 v1.1.0 + I-05 v1.1.0 with mocks;Add sample JSON responses for each endpoint;C3: I-04 lead-score contract + mock (commit 6ca606b);Review the contracts with the team | Team | Evidence openapi.yaml (or API_Contracts.docx) Postman_Collection.json GitHub_API_Contract_Commit.png 12 Oct – C3 contracts done: contracts/v1/lead-score.yaml (I-04) and contracts/v1/lead-recommendation.yaml (I-05), with real mock responses in contracts/mocks/. Shared with Saayinath (C4 Email Agent consumer).
2G80Ovxsb0a9o6MtQHEGA8kAF9IF | Review Sprint 1 progress and risks | Sprint 1 | Completed | Important | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-04 | 2026-10-04 | false | 2026-10-10 | SAAYINATH K it23304338 | 5/5 | Record lessons learned;Check the completion status of every Sprint 1 task;Identify incomplete tasks and move them to Sprint 2;Confirm the Sprint 2 plan;Update the risk register with new risks and mitigations | Team
L3DNfb9RQEu-NHNd75u1BckAEBcJ | Add authentication and secure tenant identification | Sprint 2 | Completed | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-06 | 2026-10-05 | false | 2026-10-10 | SAAYINATH K it23304338 | 6/6 | Create JWT login endpoint;Test missing and invalid JWT;Implement protected user and tenant endpoints;Test valid and invalid credentials;Implement bcrypt password verification;Create JWT verification middleware | C4 Platform-Email
d15ir2Ejp0y8X0EVS5BJm8kAJyOT | Add role-based access permissions | Sprint 2 | Completed | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-07 | 2026-10-06 | false | 2026-10-10 | SAAYINATH K it23304338 | 6/6 | Implement authorize middleware;Protect admin-only route;Test all nine role-route combinations;Protect campaign management route;Protect campaign viewing route;Define agency_admin, marketer and viewer permissions | C4 Platform-Email
b1g6dPubUEqavE0O4L3aiskAJOrB | Connect agent services through the API gateway | Sprint 2 | In progress | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-08 | 2026-10-07 | true |  |  | 0/9 | Define shared agent request and response contract;Connect Component 1 API endpoint;Connect Component 3 API endpoint;Create mock agent for unavailable services;Implement authenticated gateway proxy;Enforce roles and tenant context;Connect Component 2 API endpoint;Test successful, denied and unavailable-agent responses;Configure internal service URLs and credentials | C4 Platform-Email
tWW3Lz5eikqqko1AQ6-PhckAAchW | Record API actions in audit logs | Sprint 2 | In progress | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-09 | 2026-10-08 | true |  |  | 5/5 | Record tenant, user, action and route;Record successful API access;Verify audit records in PostgreSQL;Create audit logging middleware;Record denied API access | C4 Platform-Email
GUVHbCA7PkqbbEu18R3v7ckAM1L6 | Show each first key function to the supervisor | Sprint 2 | In progress | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-09 | 2026-10-09 | true |  |  | 0/6 | Each member prepares a demo of their first key function;Create follow-up tasks from the feedback;Schedule the meeting with the supervisor;Run the demos;Prepare a short demo order or script;Record the supervisor’s feedback | Team | Evidence Supervisor_Demo_Invite.png Demo_Screenshots.png (or the demo recording link) Supervisor_Feedback_Notes.docx
CAUKFn_9p0eQoa1HyoThaMkABDY5 | Review Sprint 2 progress and GitHub contributions | Sprint 2 | Completed | Important | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-09 | 2026-10-09 | false | 2026-10-14 | SHATHURSINI.J it23164062 | 0/5 | Check that PRs were reviewed and merged;Move unfinished tasks and plan Sprint 3;Check commits per member on GitHub;Update the risk register;Review the Sprint 2 board status | Team
YusHog_KNEi38rVn5hM3h8kAJ6Gl | Arrange the user-feedback session | Sprint 3 | In progress | Important | SAAYINATH K it23304338;JASINTHAN U it23154544;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-10 | 2026-10-10 | true |  |  |  |  | C3 Lead-Intel
35EcnmgUHkmORnMzFR-ltskALTIN | Test tenant isolation and access permissions | Sprint 3 | Completed | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-12 | 2026-10-11 | false | 2026-10-10 | SAAYINATH K it23304338 | 4/6 | Verify Tenant B can read its own records;Verify Tenant C can read its own records;Verify Tenant A can read its own records;Run RBAC tests for all roles;Verify unauthorized writes are blocked;Verify cross-tenant reads are blocked | C4 Platform-Email
k4qM_z973kysiXs_hnYkOMkAFABB | Generate a personalized three-step email sequence | Sprint 3 | In progress | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-13 | 2026-10-11 | true |  |  | 0/7 | Generate personalized subject lines and messages;Prepare tenant-specific knowledge retrieval;Configure email agent and model;Test tenant-specific generation;Save generated output and test evidence;Add safety and content checks;Define three-email sequence structure | C4 Platform-Email
TC0kO6inN0uNkshS4O9n7MkAOPSk | Connect all agents and test the complete workflow | Sprint 3 | Not started | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-14 | 2026-10-12 | true |  |  |  |  | C4 Platform-Email
NXPTfCPyvEq8vKZq-1PzMMkAB6ym | Check email privacy, consent, facts and tone | Sprint 3 | Not started | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-14 | 2026-10-13 | true |  |  |  |  | C4 Platform-Email
A46wNzBeX02RvIyc_ZhTCckADxwD | Review the 50% checkpoint with the supervisor | Sprint 3 | Not started | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-14 | 2026-10-14 | true |  |  |  |  | Team
6cEFQK5jl0Cg9BgNbRp55ckAM_50 | Compare personalized emails with generic AI emails | Sprint 4 | Not started | Important | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-17 | 2026-10-15 | true |  |  |  |  | C4 Platform-Email
3aMfr5fB2kmDcv995Gn_u8kAGu0i | Add sequence timing, consent and suppression checks | Sprint 4 | Not started | Important | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-16 | 2026-10-15 | true |  |  |  |  | C4 Platform-Email
ng9K8ZXRykm5SWUSkhQJxckAIl44 | Add monitoring, traces and alerts | Sprint 4 | Not started | Important | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-18 | 2026-10-16 | true |  |  |  |  | C4 Platform-Email
oJdPS1cdFkK0oZ8vBSPr4MkACVWd | Build the engagement model and experiment store | Sprint 4 | Not started | Important | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-19 | 2026-10-16 | true |  |  |  |  | C4 Platform-Email
gq8so08bZECDFmScnMsw-ckAKti3 | Deploy the system and test performance | Sprint 4 | Not started | Important | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-19 | 2026-10-17 | true |  |  |  |  | C4 Platform-Email
TV31rvZfMES0EYG9QHzpLskAOqsB | Test the full workflow and isolation across three tenants | Sprint 4 | Not started | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-18 | 2026-10-17 | true |  |  |  |  | Team
gElqHoOhHEeeQD0cdwKmyMkAL141 | Prepare each member’s PP1 slides | Sprint 4 | Not started | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-19 | 2026-10-17 | true |  |  |  |  | Team
Q-ddELlELU2toTK8qtU_CckAO1Oz | Prepare each member’s evidence folder | Sprint 4 | Not started | Important | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-19 | 2026-10-18 | true |  |  |  |  | Team
ILbFBYC4Y0SXQp-mKqnfoMkAOT46 | Run a timed rehearsal and practise Q&A | Sprint 4 | Not started | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-19 | 2026-10-19 | true |  |  |  |  | Team
0ZVT67QIWk-91Ea1EJ8NqskALWXL | Rehearse the presentation and demo with the supervisor | Sprint 5 | Not started | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-20 | 2026-10-20 | true |  |  |  |  | Team
lPSAySqwKk-L1aPo-MJSYckAJmri | Fix all rehearsal feedback items | Sprint 5 | Not started | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-21 | 2026-10-20 | false |  |  |  |  | Team
wWEaSgOMrECdkylZWwcNZskAEP5Q | Practise individual questions and explanations | Sprint 5 | Not started | Important | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-21 | 2026-10-20 | false |  |  |  |  | Team
WznWPEwGh0mf20UgYu20uMkANBrk | Freeze the code and test setup on a clean machine | Sprint 5 | Not started | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-21 | 2026-10-21 | false |  |  |  |  | C4 Platform-Email
oQ8dzx9J8UiOPzofV54RE8kAAKML | Finalize diaries, AI logs and PP1 submission evidence | Sprint 5 | Not started | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-22 | 2026-10-21 | false |  |  |  |  | Team
-C0Kc5Jh7kWzxY9qKakYI8kAIf9m | Add OAuth, webhooks, sync and recovery after PP1 | Backlog | Not started | Low | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 |  |  | false |  |  |  |  | C4 Platform-Email
NsSUAVg4VEChXYGsDLToDskAHv8Z | Optional: add tenant opt-in settings and API | Backlog | Not started | Low | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 |  |  | false |  |  |  |  | C4 Platform-Email

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
s6C-ZlJ_EEmKKIxjtc9IQMkAHxjj | Set up the tenant database and sample tenants | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-01 | 2026-10-01 |  | false | 2026-10-09 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 7/7 | Create PostgreSQL database using Docker;Configure Row-Level Security policies;Create three sample tenants;Create restricted application database role;Enable pgvector and UUID extensions;Run tenant isolation tests;Create tenants, users, knowledge_base and audit_log tables | C4 Platform-Email | PostgreSQL database initialized with pgvector, three sample tenants, tenant-aware tables and RLS policies. Restricted application role configured. Initial tenant isolation tests passed. Development security hardening remains necessary before production deployment.
Tebj5Z6QvU-SkCkqfGl5_8kALvN6 | Set up the team GitHub repository | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-01 | 2026-10-01 |  | false | 2026-10-08 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 5/5 | Create Repository;Add Collabrators;Verify Team Repository Access;Create Branches;Protect Main Branch | Team
K0IRlzBiPESovq7UxQO9RMkAPHa4 | Meet the supervisor to approve scope and Finalize the Individual Report | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-09-15 | 2026-09-14 |  | false | 2026-10-09 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 3/3 | Create Individual Reports;Discuss with the Supervisor;Get Supervisor Signature | Team | Completed on 14th September
dvN4Bp4-KkKQe7Aqo54-C8kAKMfB | Set up Planner and add Sprint 1 and 2 tasks | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-01 | 2026-10-01 |  | false | 2026-10-09 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 4/4 | Create Planner;Assign People;Create Sprints;Add Tasks | Team
509o6p7yikitvlPbyR7PJskAM4z6 | Create diary and AI-use log templates | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-02 | 2026-10-01 |  | false | 2026-10-20 | d7043cfa-51ae-4438-9d08-62b6899b4ebc | 0/4 | Each member fills in their first entry;Create the weekly diary template (date, attendees, work done, issues, next steps);Create the AI-use log template (date, tool, purpose, prompt summary, how the output was used, how it;Upload both templates to the team SharePoint folder | Team | Evidence Diary_Template.docx AI_Use_Log_Template.xlsx SharePoint_Templates_Folder.png
CQQEW_of-0eHfsbhnzLXuMkAOfC6 | Agree and record key project decisions | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-02 | 2026-10-01 |  | false | 2026-10-10 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 6/6 | Agree on the multi-tenant approach (tenant identification, data isolation);Agree on GitHub branching, commit and PR review rules;All members confirm the decisions;Record the decisions in a decision log;Agree on the tech stack and frameworks;Hold a team decision meeting | Team | Evidence Decision_Log.xlsx (decision, reason, date, agreed by) Decision_Meeting_Minutes.docx Teams_Meeting_Attendance.png
bRMfwq5CIEK8RBSyaDHxU8kALbNy | Define API contracts and sample responses | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-04 | 2026-10-02 |  | false | 2026-10-20 | d7043cfa-51ae-4438-9d08-62b6899b4ebc | 4/11 | C3: I-05 contract + mock;Define the standard error format and status codes;Define request and response schemas;List the endpoints for each component;C3: I-05 lead-recommendation contract + mock (commit 89781CD;Define the auth and tenant ID headers;Commit the contracts to GitHub;C3 I-04 v1.1.0 + I-05 v1.1.0 with mocks;Add sample JSON responses for each endpoint;C3: I-04 lead-score contract + mock (commit 6ca606b);Review the contracts with the team | Team | Evidence openapi.yaml (or API_Contracts.docx) Postman_Collection.json GitHub_API_Contract_Commit.png 12 Oct – C3 contracts done: contracts/v1/lead-score.yaml (I-04) and contracts/v1/lead-recommendation.yaml (I-05), with real mock responses in contracts/mocks/. Shared with Saayinath (C4 Email Agent consumer).
2G80Ovxsb0a9o6MtQHEGA8kAF9IF | Review Sprint 1 progress and risks | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-04 | 2026-10-04 |  | false | 2026-10-10 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 5/5 | Record lessons learned;Check the completion status of every Sprint 1 task;Identify incomplete tasks and move them to Sprint 2;Confirm the Sprint 2 plan;Update the risk register with new risks and mitigations | Team
L3DNfb9RQEu-NHNd75u1BckAEBcJ | Add authentication and secure tenant identification | lvLKROICTE27IWeJgriNxckAMs2W |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-06 | 2026-10-05 |  | false | 2026-10-10 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 6/6 | Create JWT login endpoint;Test missing and invalid JWT;Implement protected user and tenant endpoints;Test valid and invalid credentials;Implement bcrypt password verification;Create JWT verification middleware | C4 Platform-Email
d15ir2Ejp0y8X0EVS5BJm8kAJyOT | Add role-based access permissions | lvLKROICTE27IWeJgriNxckAMs2W |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-07 | 2026-10-06 |  | false | 2026-10-10 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 6/6 | Implement authorize middleware;Protect admin-only route;Test all nine role-route combinations;Protect campaign management route;Protect campaign viewing route;Define agency_admin, marketer and viewer permissions | C4 Platform-Email
b1g6dPubUEqavE0O4L3aiskAJOrB | Connect agent services through the API gateway | lvLKROICTE27IWeJgriNxckAMs2W |  | In progress | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-08 | 2026-10-07 |  | true |  |  | 0/9 | Define shared agent request and response contract;Connect Component 1 API endpoint;Connect Component 3 API endpoint;Create mock agent for unavailable services;Implement authenticated gateway proxy;Enforce roles and tenant context;Connect Component 2 API endpoint;Test successful, denied and unavailable-agent responses;Configure internal service URLs and credentials | C4 Platform-Email
tWW3Lz5eikqqko1AQ6-PhckAAchW | Record API actions in audit logs | lvLKROICTE27IWeJgriNxckAMs2W |  | In progress | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-09 | 2026-10-08 |  | true |  |  | 5/5 | Record tenant, user, action and route;Record successful API access;Verify audit records in PostgreSQL;Create audit logging middleware;Record denied API access | C4 Platform-Email
GUVHbCA7PkqbbEu18R3v7ckAM1L6 | Show each first key function to the supervisor | lvLKROICTE27IWeJgriNxckAMs2W |  | In progress | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-09 | 2026-10-09 |  | true |  |  | 0/6 | Each member prepares a demo of their first key function;Create follow-up tasks from the feedback;Schedule the meeting with the supervisor;Run the demos;Prepare a short demo order or script;Record the supervisor’s feedback | Team | Evidence Supervisor_Demo_Invite.png Demo_Screenshots.png (or the demo recording link) Supervisor_Feedback_Notes.docx
CAUKFn_9p0eQoa1HyoThaMkABDY5 | Review Sprint 2 progress and GitHub contributions | lvLKROICTE27IWeJgriNxckAMs2W |  | Completed | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-09 | 2026-10-09 |  | false | 2026-10-14 | d7043cfa-51ae-4438-9d08-62b6899b4ebc | 0/5 | Check that PRs were reviewed and merged;Move unfinished tasks and plan Sprint 3;Check commits per member on GitHub;Update the risk register;Review the Sprint 2 board status | Team
YusHog_KNEi38rVn5hM3h8kAJ6Gl | Arrange the user-feedback session | XGKGyDgqAESDK8e2D43hN8kACEeA |  | In progress | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-10 | 2026-10-10 |  | true |  |  |  |  | C3 Lead-Intel
35EcnmgUHkmORnMzFR-ltskALTIN | Test tenant isolation and access permissions | XGKGyDgqAESDK8e2D43hN8kACEeA |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-12 | 2026-10-11 |  | false | 2026-10-10 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 4/6 | Verify Tenant B can read its own records;Verify Tenant C can read its own records;Verify Tenant A can read its own records;Run RBAC tests for all roles;Verify unauthorized writes are blocked;Verify cross-tenant reads are blocked | C4 Platform-Email
k4qM_z973kysiXs_hnYkOMkAFABB | Generate a personalized three-step email sequence | XGKGyDgqAESDK8e2D43hN8kACEeA |  | In progress | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-13 | 2026-10-11 |  | true |  |  | 0/7 | Generate personalized subject lines and messages;Prepare tenant-specific knowledge retrieval;Configure email agent and model;Test tenant-specific generation;Save generated output and test evidence;Add safety and content checks;Define three-email sequence structure | C4 Platform-Email
TC0kO6inN0uNkshS4O9n7MkAOPSk | Connect all agents and test the complete workflow | XGKGyDgqAESDK8e2D43hN8kACEeA |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-14 | 2026-10-12 |  | true |  |  |  |  | C4 Platform-Email
NXPTfCPyvEq8vKZq-1PzMMkAB6ym | Check email privacy, consent, facts and tone | XGKGyDgqAESDK8e2D43hN8kACEeA |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-14 | 2026-10-13 |  | true |  |  |  |  | C4 Platform-Email
A46wNzBeX02RvIyc_ZhTCckADxwD | Review the 50% checkpoint with the supervisor | XGKGyDgqAESDK8e2D43hN8kACEeA |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-14 | 2026-10-14 |  | true |  |  |  |  | Team
6cEFQK5jl0Cg9BgNbRp55ckAM_50 | Compare personalized emails with generic AI emails | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-17 | 2026-10-15 |  | true |  |  |  |  | C4 Platform-Email
3aMfr5fB2kmDcv995Gn_u8kAGu0i | Add sequence timing, consent and suppression checks | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-16 | 2026-10-15 |  | true |  |  |  |  | C4 Platform-Email
ng9K8ZXRykm5SWUSkhQJxckAIl44 | Add monitoring, traces and alerts | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-18 | 2026-10-16 |  | true |  |  |  |  | C4 Platform-Email
oJdPS1cdFkK0oZ8vBSPr4MkACVWd | Build the engagement model and experiment store | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-19 | 2026-10-16 |  | true |  |  |  |  | C4 Platform-Email
gq8so08bZECDFmScnMsw-ckAKti3 | Deploy the system and test performance | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-19 | 2026-10-17 |  | true |  |  |  |  | C4 Platform-Email
TV31rvZfMES0EYG9QHzpLskAOqsB | Test the full workflow and isolation across three tenants | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-18 | 2026-10-17 |  | true |  |  |  |  | Team
gElqHoOhHEeeQD0cdwKmyMkAL141 | Prepare each member’s PP1 slides | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-19 | 2026-10-17 |  | true |  |  |  |  | Team
Q-ddELlELU2toTK8qtU_CckAO1Oz | Prepare each member’s evidence folder | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-19 | 2026-10-18 |  | true |  |  |  |  | Team
ILbFBYC4Y0SXQp-mKqnfoMkAOT46 | Run a timed rehearsal and practise Q&A | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-19 | 2026-10-19 |  | true |  |  |  |  | Team
0ZVT67QIWk-91Ea1EJ8NqskALWXL | Rehearse the presentation and demo with the supervisor | FBkAtFWwAEmbTJ_6EVpCZckAKkTB |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-20 | 2026-10-20 |  | true |  |  |  |  | Team
lPSAySqwKk-L1aPo-MJSYckAJmri | Fix all rehearsal feedback items | FBkAtFWwAEmbTJ_6EVpCZckAKkTB |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-21 | 2026-10-20 |  | false |  |  |  |  | Team
wWEaSgOMrECdkylZWwcNZskAEP5Q | Practise individual questions and explanations | FBkAtFWwAEmbTJ_6EVpCZckAKkTB |  | Not started | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-21 | 2026-10-20 |  | false |  |  |  |  | Team
WznWPEwGh0mf20UgYu20uMkANBrk | Freeze the code and test setup on a clean machine | FBkAtFWwAEmbTJ_6EVpCZckAKkTB |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-21 | 2026-10-21 |  | false |  |  |  |  | C4 Platform-Email
oQ8dzx9J8UiOPzofV54RE8kAAKML | Finalize diaries, AI logs and PP1 submission evidence | FBkAtFWwAEmbTJ_6EVpCZckAKkTB |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-22 | 2026-10-21 |  | false |  |  |  |  | Team
-C0Kc5Jh7kWzxY9qKakYI8kAIf9m | Add OAuth, webhooks, sync and recovery after PP1 | nKY5vO1bg0u2XVpzDOmXsskAIDSz |  | Not started | Low | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 |  |  |  | false |  |  |  |  | C4 Platform-Email
NsSUAVg4VEChXYGsDLToDskAHv8Z | Optional: add tenant opt-in settings and API | nKY5vO1bg0u2XVpzDOmXsskAIDSz |  | Not started | Low | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 |  |  |  | false |  |  |  |  | C4 Platform-Email

## Buckets
Bucket ID | Bucket Name
nKY5vO1bg0u2XVpzDOmXsskAIDSz | Backlog
wHDew6aBm0qh2FuzAUEQAskAFS3E | Sprint 1
lvLKROICTE27IWeJgriNxckAMs2W | Sprint 2
XGKGyDgqAESDK8e2D43hN8kACEeA | Sprint 3
Mejb9NoRrkOXkOK0E9EoiskACnL9 | Sprint 4
FBkAtFWwAEmbTJ_6EVpCZckAKkTB | Sprint 5

## Users
User ID | User Name | Email
cc6f3715-42e2-48b1-80c1-1f8982decf2f | SAAYINATH K it23304338 | it23304338@my.sliit.lk
79aafd74-8432-4a9b-991d-08a7ef7b1a22 | JASINTHAN U it23154544 | it23154544@my.sliit.lk
11f012a9-8e1d-427d-bcf3-f252787021c2 | SRIRAMANA S it23136724 | it23136724@my.sliit.lk
d7043cfa-51ae-4438-9d08-62b6899b4ebc | SHATHURSINI.J it23164062 | it23164062@my.sliit.lk