## Consolidated Data
Task ID | Task Name | Bucket | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
s6C-ZlJ_EEmKKIxjtc9IQMkAHxjj | Set up the tenant database and sample tenants | Sprint 1 | Completed | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-01 | 2026-10-01 | false | 2026-10-09 | SAAYINATH K it23304338 | 7/7 | Create PostgreSQL database using Docker;Configure Row-Level Security policies;Create three sample tenants;Create restricted application database role;Enable pgvector and UUID extensions;Run tenant isolation tests;Create tenants, users, knowledge_base and audit_log tables | C4 Platform-Email | PostgreSQL database initialized with pgvector, three sample tenants, tenant-aware tables and RLS policies. Restricted application role configured. Initial tenant isolation tests passed. Development security hardening remains necessary before production deployment.
Tebj5Z6QvU-SkCkqfGl5_8kALvN6 | Set up the team GitHub repository | Sprint 1 | Completed | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-01 | 2026-10-01 | false | 2026-10-08 | SAAYINATH K it23304338 | 5/5 | Create Repository;Add Collabrators;Verify Team Repository Access;Create Branches;Protect Main Branch | Team
K0IRlzBiPESovq7UxQO9RMkAPHa4 | Meet the supervisor to approve scope and Finalize the Individual Report | Sprint 1 | Completed | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-07 | 2026-09-15 | 2026-09-14 | false | 2026-10-09 | SAAYINATH K it23304338 | 3/3 | Create Individual Reports;Discuss with the Supervisor;Get Supervisor Signature | Team | Completed on 14th September
dvN4Bp4-KkKQe7Aqo54-C8kAKMfB | Set up Planner and add Sprint 1 and 2 tasks | Sprint 1 | Completed | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-01 | 2026-10-01 | false | 2026-10-09 | SAAYINATH K it23304338 | 4/4 | Create Planner;Assign People;Create Sprints;Add Tasks | Team
509o6p7yikitvlPbyR7PJskAM4z6 | Create diary and AI-use log templates | Sprint 1 | Completed | Important | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-02 | 2026-10-01 | false | 2026-10-20 | SHATHURSINI.J it23164062 | 0/4 | Each member fills in their first entry;Create the weekly diary template (date, attendees, work done, issues, next steps);Create the AI-use log template (date, tool, purpose, prompt summary, how the output was used, how it;Upload both templates to the team SharePoint folder | Team | Evidence Diary_Template.docx AI_Use_Log_Template.xlsx SharePoint_Templates_Folder.png
CQQEW_of-0eHfsbhnzLXuMkAOfC6 | Agree and record key project decisions | Sprint 1 | Completed | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-02 | 2026-10-01 | false | 2026-10-10 | SAAYINATH K it23304338 | 6/6 | Agree on the multi-tenant approach (tenant identification, data isolation);Agree on GitHub branching, commit and PR review rules;All members confirm the decisions;Record the decisions in a decision log;Agree on the tech stack and frameworks;Hold a team decision meeting | Team | Evidence Decision_Log.xlsx (decision, reason, date, agreed by) Decision_Meeting_Minutes.docx Teams_Meeting_Attendance.png
bRMfwq5CIEK8RBSyaDHxU8kALbNy | Define API contracts and sample responses | Sprint 1 | Completed | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-04 | 2026-10-02 | false | 2026-10-20 | SHATHURSINI.J it23164062 | 4/11 | C3: I-05 contract + mock;Define the standard error format and status codes;Define request and response schemas;List the endpoints for each component;C3: I-05 lead-recommendation contract + mock (commit 89781CD;Define the auth and tenant ID headers;Commit the contracts to GitHub;C3 I-04 v1.1.0 + I-05 v1.1.0 with mocks;Add sample JSON responses for each endpoint;C3: I-04 lead-score contract + mock (commit 6ca606b);Review the contracts with the team | Team | Evidence openapi.yaml (or API_Contracts.docx) Postman_Collection.json GitHub_API_Contract_Commit.png 12 Oct – C3 contracts done: contracts/v1/lead-score.yaml (I-04) and contracts/v1/lead-recommendation.yaml (I-05), with real mock responses in contracts/mocks/. Shared with Saayinath (C4 Email Agent consumer).
2G80Ovxsb0a9o6MtQHEGA8kAF9IF | Review Sprint 1 progress and risks | Sprint 1 | Completed | Important | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-04 | 2026-10-04 | false | 2026-10-10 | SAAYINATH K it23304338 | 5/5 | Record lessons learned;Check the completion status of every Sprint 1 task;Identify incomplete tasks and move them to Sprint 2;Confirm the Sprint 2 plan;Update the risk register with new risks and mitigations | Team
L3DNfb9RQEu-NHNd75u1BckAEBcJ | Add authentication and secure tenant identification | Sprint 2 | Completed | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-06 | 2026-10-05 | false | 2026-10-10 | SAAYINATH K it23304338 | 6/6 | Create JWT login endpoint;Test missing and invalid JWT;Implement protected user and tenant endpoints;Test valid and invalid credentials;Implement bcrypt password verification;Create JWT verification middleware | C4 Platform-Email
d15ir2Ejp0y8X0EVS5BJm8kAJyOT | Add role-based access permissions | Sprint 2 | Completed | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-07 | 2026-10-06 | false | 2026-10-10 | SAAYINATH K it23304338 | 6/6 | Implement authorize middleware;Protect admin-only route;Test all nine role-route combinations;Protect campaign management route;Protect campaign viewing route;Define agency_admin, marketer and viewer permissions | C4 Platform-Email
b1g6dPubUEqavE0O4L3aiskAJOrB | Connect agent services through the API gateway | Sprint 2 | In progress | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-07 | 2026-10-08 | 2026-10-07 | true |  |  | 0/9 | Define shared agent request and response contract;Connect Component 1 API endpoint;Connect Component 3 API endpoint;Create mock agent for unavailable services;Implement authenticated gateway proxy;Enforce roles and tenant context;Connect Component 2 API endpoint;Test successful, denied and unavailable-agent responses;Configure internal service URLs and credentials | C4 Platform-Email
tWW3Lz5eikqqko1AQ6-PhckAAchW | Record API actions in audit logs | Sprint 2 | In progress | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-09 | 2026-10-08 | true |  |  | 5/5 | Record tenant, user, action and route;Record successful API access;Verify audit records in PostgreSQL;Create audit logging middleware;Record denied API access | C4 Platform-Email
GUVHbCA7PkqbbEu18R3v7ckAM1L6 | Show each first key function to the supervisor | Sprint 2 | In progress | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-09 | 2026-10-09 | true |  |  | 0/6 | Each member prepares a demo of their first key function;Create follow-up tasks from the feedback;Schedule the meeting with the supervisor;Run the demos;Prepare a short demo order or script;Record the supervisor’s feedback | Team | Evidence Supervisor_Demo_Invite.png Demo_Screenshots.png (or the demo recording link) Supervisor_Feedback_Notes.docx
CAUKFn_9p0eQoa1HyoThaMkABDY5 | Review Sprint 2 progress and GitHub contributions | Sprint 2 | Completed | Important | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-09 | 2026-10-09 | false | 2026-10-14 | SHATHURSINI.J it23164062 | 0/5 | Check that PRs were reviewed and merged;Move unfinished tasks and plan Sprint 3;Check commits per member on GitHub;Update the risk register;Review the Sprint 2 board status | Team
YusHog_KNEi38rVn5hM3h8kAJ6Gl | Arrange the user-feedback session | Sprint 3 | In progress | Important | SAAYINATH K it23304338;JASINTHAN U it23154544;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-10 | 2026-10-10 | true |  |  |  |  | C3 Lead-Intel
35EcnmgUHkmORnMzFR-ltskALTIN | Test tenant isolation and access permissions | Sprint 3 | Completed | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-12 | 2026-10-11 | false | 2026-10-10 | SAAYINATH K it23304338 | 4/6 | Verify Tenant B can read its own records;Verify Tenant C can read its own records;Verify Tenant A can read its own records;Run RBAC tests for all roles;Verify unauthorized writes are blocked;Verify cross-tenant reads are blocked | C4 Platform-Email
k4qM_z973kysiXs_hnYkOMkAFABB | Generate a personalized three-step email sequence | Sprint 3 | In progress | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-13 | 2026-10-11 | true |  |  | 0/7 | Generate personalized subject lines and messages;Prepare tenant-specific knowledge retrieval;Configure email agent and model;Test tenant-specific generation;Save generated output and test evidence;Add safety and content checks;Define three-email sequence structure | C4 Platform-Email
TC0kO6inN0uNkshS4O9n7MkAOPSk | Connect all agents and test the complete workflow | Sprint 3 | Not started | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-14 | 2026-10-12 | true |  |  |  |  | C4 Platform-Email
NXPTfCPyvEq8vKZq-1PzMMkAB6ym | Check email privacy, consent, facts and tone | Sprint 3 | Not started | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-14 | 2026-10-13 | true |  |  |  |  | C4 Platform-Email
A46wNzBeX02RvIyc_ZhTCckADxwD | Review the 50% checkpoint with the supervisor | Sprint 3 | Not started | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-14 | 2026-10-14 | true |  |  |  |  | Team
6cEFQK5jl0Cg9BgNbRp55ckAM_50 | Compare personalized emails with generic AI emails | Sprint 4 | Not started | Important | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-17 | 2026-10-15 | true |  |  |  |  | C4 Platform-Email
3aMfr5fB2kmDcv995Gn_u8kAGu0i | Add sequence timing, consent and suppression checks | Sprint 4 | Not started | Important | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-16 | 2026-10-15 | true |  |  |  |  | C4 Platform-Email
ng9K8ZXRykm5SWUSkhQJxckAIl44 | Add monitoring, traces and alerts | Sprint 4 | Not started | Important | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-18 | 2026-10-16 | true |  |  |  |  | C4 Platform-Email
oJdPS1cdFkK0oZ8vBSPr4MkACVWd | Build the engagement model and experiment store | Sprint 4 | Not started | Important | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-19 | 2026-10-16 | true |  |  |  |  | C4 Platform-Email
gq8so08bZECDFmScnMsw-ckAKti3 | Deploy the system and test performance | Sprint 4 | Not started | Important | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-19 | 2026-10-17 | true |  |  |  |  | C4 Platform-Email
TV31rvZfMES0EYG9QHzpLskAOqsB | Test the full workflow and isolation across three tenants | Sprint 4 | Not started | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-18 | 2026-10-17 | true |  |  |  |  | Team
gElqHoOhHEeeQD0cdwKmyMkAL141 | Prepare each member’s PP1 slides | Sprint 4 | Not started | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-19 | 2026-10-17 | true |  |  |  |  | Team
Q-ddELlELU2toTK8qtU_CckAO1Oz | Prepare each member’s evidence folder | Sprint 4 | Not started | Important | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-19 | 2026-10-18 | true |  |  |  |  | Team
ILbFBYC4Y0SXQp-mKqnfoMkAOT46 | Run a timed rehearsal and practise Q&A | Sprint 4 | Not started | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-19 | 2026-10-19 | true |  |  |  |  | Team
0ZVT67QIWk-91Ea1EJ8NqskALWXL | Rehearse the presentation and demo with the supervisor | Sprint 5 | Not started | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-20 | 2026-10-20 | true |  |  |  |  | Team
lPSAySqwKk-L1aPo-MJSYckAJmri | Fix all rehearsal feedback items | Sprint 5 | Not started | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-21 | 2026-10-20 | false |  |  |  |  | Team
wWEaSgOMrECdkylZWwcNZskAEP5Q | Practise individual questions and explanations | Sprint 5 | Not started | Important | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-21 | 2026-10-20 | false |  |  |  |  | Team
WznWPEwGh0mf20UgYu20uMkANBrk | Freeze the code and test setup on a clean machine | Sprint 5 | Not started | Urgent | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-21 | 2026-10-21 | false |  |  |  |  | C4 Platform-Email
oQ8dzx9J8UiOPzofV54RE8kAAKML | Finalize diaries, AI logs and PP1 submission evidence | Sprint 5 | Not started | Urgent | SAAYINATH K it23304338;JASINTHAN U it23154544;SRIRAMANA S it23136724;SHATHURSINI.J it23164062 | SAAYINATH K it23304338 | 2026-10-01 | 2026-10-22 | 2026-10-21 | false |  |  |  |  | Team
-C0Kc5Jh7kWzxY9qKakYI8kAIf9m | Add OAuth, webhooks, sync and recovery after PP1 | Backlog | Not started | Low | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 |  |  | false |  |  |  |  | C4 Platform-Email
NsSUAVg4VEChXYGsDLToDskAHv8Z | Optional: add tenant opt-in settings and API | Backlog | Not started | Low | SAAYINATH K it23304338 | SAAYINATH K it23304338 | 2026-10-01 |  |  | false |  |  |  |  | C4 Platform-Email

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
s6C-ZlJ_EEmKKIxjtc9IQMkAHxjj | Set up the tenant database and sample tenants | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-01 | 2026-10-01 |  | false | 2026-10-09 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 7/7 | Create PostgreSQL database using Docker;Configure Row-Level Security policies;Create three sample tenants;Create restricted application database role;Enable pgvector and UUID extensions;Run tenant isolation tests;Create tenants, users, knowledge_base and audit_log tables | C4 Platform-Email | PostgreSQL database initialized with pgvector, three sample tenants, tenant-aware tables and RLS policies. Restricted application role configured. Initial tenant isolation tests passed. Development security hardening remains necessary before production deployment.
Tebj5Z6QvU-SkCkqfGl5_8kALvN6 | Set up the team GitHub repository | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-01 | 2026-10-01 |  | false | 2026-10-08 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 5/5 | Create Repository;Add Collabrators;Verify Team Repository Access;Create Branches;Protect Main Branch | Team
K0IRlzBiPESovq7UxQO9RMkAPHa4 | Meet the supervisor to approve scope and Finalize the Individual Report | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-09-15 | 2026-09-14 |  | false | 2026-10-09 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 3/3 | Create Individual Reports;Discuss with the Supervisor;Get Supervisor Signature | Team | Completed on 14th September
dvN4Bp4-KkKQe7Aqo54-C8kAKMfB | Set up Planner and add Sprint 1 and 2 tasks | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-01 | 2026-10-01 |  | false | 2026-10-09 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 4/4 | Create Planner;Assign People;Create Sprints;Add Tasks | Team
509o6p7yikitvlPbyR7PJskAM4z6 | Create diary and AI-use log templates | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-02 | 2026-10-01 |  | false | 2026-10-20 | d7043cfa-51ae-4438-9d08-62b6899b4ebc | 0/4 | Each member fills in their first entry;Create the weekly diary template (date, attendees, work done, issues, next steps);Create the AI-use log template (date, tool, purpose, prompt summary, how the output was used, how it;Upload both templates to the team SharePoint folder | Team | Evidence Diary_Template.docx AI_Use_Log_Template.xlsx SharePoint_Templates_Folder.png
CQQEW_of-0eHfsbhnzLXuMkAOfC6 | Agree and record key project decisions | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-02 | 2026-10-01 |  | false | 2026-10-10 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 6/6 | Agree on the multi-tenant approach (tenant identification, data isolation);Agree on GitHub branching, commit and PR review rules;All members confirm the decisions;Record the decisions in a decision log;Agree on the tech stack and frameworks;Hold a team decision meeting | Team | Evidence Decision_Log.xlsx (decision, reason, date, agreed by) Decision_Meeting_Minutes.docx Teams_Meeting_Attendance.png
bRMfwq5CIEK8RBSyaDHxU8kALbNy | Define API contracts and sample responses | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-04 | 2026-10-02 |  | false | 2026-10-20 | d7043cfa-51ae-4438-9d08-62b6899b4ebc | 4/11 | C3: I-05 contract + mock;Define the standard error format and status codes;Define request and response schemas;List the endpoints for each component;C3: I-05 lead-recommendation contract + mock (commit 89781CD;Define the auth and tenant ID headers;Commit the contracts to GitHub;C3 I-04 v1.1.0 + I-05 v1.1.0 with mocks;Add sample JSON responses for each endpoint;C3: I-04 lead-score contract + mock (commit 6ca606b);Review the contracts with the team | Team | Evidence openapi.yaml (or API_Contracts.docx) Postman_Collection.json GitHub_API_Contract_Commit.png 12 Oct – C3 contracts done: contracts/v1/lead-score.yaml (I-04) and contracts/v1/lead-recommendation.yaml (I-05), with real mock responses in contracts/mocks/. Shared with Saayinath (C4 Email Agent consumer).
2G80Ovxsb0a9o6MtQHEGA8kAF9IF | Review Sprint 1 progress and risks | wHDew6aBm0qh2FuzAUEQAskAFS3E |  | Completed | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-04 | 2026-10-04 |  | false | 2026-10-10 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 5/5 | Record lessons learned;Check the completion status of every Sprint 1 task;Identify incomplete tasks and move them to Sprint 2;Confirm the Sprint 2 plan;Update the risk register with new risks and mitigations | Team
L3DNfb9RQEu-NHNd75u1BckAEBcJ | Add authentication and secure tenant identification | lvLKROICTE27IWeJgriNxckAMs2W |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-06 | 2026-10-05 |  | false | 2026-10-10 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 6/6 | Create JWT login endpoint;Test missing and invalid JWT;Implement protected user and tenant endpoints;Test valid and invalid credentials;Implement bcrypt password verification;Create JWT verification middleware | C4 Platform-Email
d15ir2Ejp0y8X0EVS5BJm8kAJyOT | Add role-based access permissions | lvLKROICTE27IWeJgriNxckAMs2W |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-07 | 2026-10-06 |  | false | 2026-10-10 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 6/6 | Implement authorize middleware;Protect admin-only route;Test all nine role-route combinations;Protect campaign management route;Protect campaign viewing route;Define agency_admin, marketer and viewer permissions | C4 Platform-Email
b1g6dPubUEqavE0O4L3aiskAJOrB | Connect agent services through the API gateway | lvLKROICTE27IWeJgriNxckAMs2W |  | In progress | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-07 | 2026-10-08 | 2026-10-07 |  | true |  |  | 0/9 | Define shared agent request and response contract;Connect Component 1 API endpoint;Connect Component 3 API endpoint;Create mock agent for unavailable services;Implement authenticated gateway proxy;Enforce roles and tenant context;Connect Component 2 API endpoint;Test successful, denied and unavailable-agent responses;Configure internal service URLs and credentials | C4 Platform-Email
tWW3Lz5eikqqko1AQ6-PhckAAchW | Record API actions in audit logs | lvLKROICTE27IWeJgriNxckAMs2W |  | In progress | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-09 | 2026-10-08 |  | true |  |  | 5/5 | Record tenant, user, action and route;Record successful API access;Verify audit records in PostgreSQL;Create audit logging middleware;Record denied API access | C4 Platform-Email
GUVHbCA7PkqbbEu18R3v7ckAM1L6 | Show each first key function to the supervisor | lvLKROICTE27IWeJgriNxckAMs2W |  | In progress | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-09 | 2026-10-09 |  | true |  |  | 0/6 | Each member prepares a demo of their first key function;Create follow-up tasks from the feedback;Schedule the meeting with the supervisor;Run the demos;Prepare a short demo order or script;Record the supervisor’s feedback | Team | Evidence Supervisor_Demo_Invite.png Demo_Screenshots.png (or the demo recording link) Supervisor_Feedback_Notes.docx
CAUKFn_9p0eQoa1HyoThaMkABDY5 | Review Sprint 2 progress and GitHub contributions | lvLKROICTE27IWeJgriNxckAMs2W |  | Completed | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-09 | 2026-10-09 |  | false | 2026-10-14 | d7043cfa-51ae-4438-9d08-62b6899b4ebc | 0/5 | Check that PRs were reviewed and merged;Move unfinished tasks and plan Sprint 3;Check commits per member on GitHub;Update the risk register;Review the Sprint 2 board status | Team
YusHog_KNEi38rVn5hM3h8kAJ6Gl | Arrange the user-feedback session | XGKGyDgqAESDK8e2D43hN8kACEeA |  | In progress | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-10 | 2026-10-10 |  | true |  |  |  |  | C3 Lead-Intel
35EcnmgUHkmORnMzFR-ltskALTIN | Test tenant isolation and access permissions | XGKGyDgqAESDK8e2D43hN8kACEeA |  | Completed | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-12 | 2026-10-11 |  | false | 2026-10-10 | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 4/6 | Verify Tenant B can read its own records;Verify Tenant C can read its own records;Verify Tenant A can read its own records;Run RBAC tests for all roles;Verify unauthorized writes are blocked;Verify cross-tenant reads are blocked | C4 Platform-Email
k4qM_z973kysiXs_hnYkOMkAFABB | Generate a personalized three-step email sequence | XGKGyDgqAESDK8e2D43hN8kACEeA |  | In progress | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-13 | 2026-10-11 |  | true |  |  | 0/7 | Generate personalized subject lines and messages;Prepare tenant-specific knowledge retrieval;Configure email agent and model;Test tenant-specific generation;Save generated output and test evidence;Add safety and content checks;Define three-email sequence structure | C4 Platform-Email
TC0kO6inN0uNkshS4O9n7MkAOPSk | Connect all agents and test the complete workflow | XGKGyDgqAESDK8e2D43hN8kACEeA |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-14 | 2026-10-12 |  | true |  |  |  |  | C4 Platform-Email
NXPTfCPyvEq8vKZq-1PzMMkAB6ym | Check email privacy, consent, facts and tone | XGKGyDgqAESDK8e2D43hN8kACEeA |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-14 | 2026-10-13 |  | true |  |  |  |  | C4 Platform-Email
A46wNzBeX02RvIyc_ZhTCckADxwD | Review the 50% checkpoint with the supervisor | XGKGyDgqAESDK8e2D43hN8kACEeA |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-14 | 2026-10-14 |  | true |  |  |  |  | Team
6cEFQK5jl0Cg9BgNbRp55ckAM_50 | Compare personalized emails with generic AI emails | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-17 | 2026-10-15 |  | true |  |  |  |  | C4 Platform-Email
3aMfr5fB2kmDcv995Gn_u8kAGu0i | Add sequence timing, consent and suppression checks | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-16 | 2026-10-15 |  | true |  |  |  |  | C4 Platform-Email
ng9K8ZXRykm5SWUSkhQJxckAIl44 | Add monitoring, traces and alerts | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-18 | 2026-10-16 |  | true |  |  |  |  | C4 Platform-Email
oJdPS1cdFkK0oZ8vBSPr4MkACVWd | Build the engagement model and experiment store | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-19 | 2026-10-16 |  | true |  |  |  |  | C4 Platform-Email
gq8so08bZECDFmScnMsw-ckAKti3 | Deploy the system and test performance | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-19 | 2026-10-17 |  | true |  |  |  |  | C4 Platform-Email
TV31rvZfMES0EYG9QHzpLskAOqsB | Test the full workflow and isolation across three tenants | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-18 | 2026-10-17 |  | true |  |  |  |  | Team
gElqHoOhHEeeQD0cdwKmyMkAL141 | Prepare each member’s PP1 slides | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-19 | 2026-10-17 |  | true |  |  |  |  | Team
Q-ddELlELU2toTK8qtU_CckAO1Oz | Prepare each member’s evidence folder | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-19 | 2026-10-18 |  | true |  |  |  |  | Team
ILbFBYC4Y0SXQp-mKqnfoMkAOT46 | Run a timed rehearsal and practise Q&A | Mejb9NoRrkOXkOK0E9EoiskACnL9 |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-19 | 2026-10-19 |  | true |  |  |  |  | Team
0ZVT67QIWk-91Ea1EJ8NqskALWXL | Rehearse the presentation and demo with the supervisor | FBkAtFWwAEmbTJ_6EVpCZckAKkTB |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-20 | 2026-10-20 |  | true |  |  |  |  | Team
lPSAySqwKk-L1aPo-MJSYckAJmri | Fix all rehearsal feedback items | FBkAtFWwAEmbTJ_6EVpCZckAKkTB |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-21 | 2026-10-20 |  | false |  |  |  |  | Team
wWEaSgOMrECdkylZWwcNZskAEP5Q | Practise individual questions and explanations | FBkAtFWwAEmbTJ_6EVpCZckAKkTB |  | Not started | Important | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-21 | 2026-10-20 |  | false |  |  |  |  | Team
WznWPEwGh0mf20UgYu20uMkANBrk | Freeze the code and test setup on a clean machine | FBkAtFWwAEmbTJ_6EVpCZckAKkTB |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-21 | 2026-10-21 |  | false |  |  |  |  | C4 Platform-Email
oQ8dzx9J8UiOPzofV54RE8kAAKML | Finalize diaries, AI logs and PP1 submission evidence | FBkAtFWwAEmbTJ_6EVpCZckAKkTB |  | Not started | Urgent | cc6f3715-42e2-48b1-80c1-1f8982decf2f;79aafd74-8432-4a9b-991d-08a7ef7b1a22;11f012a9-8e1d-427d-bcf3-f252787021c2;d7043cfa-51ae-4438-9d08-62b6899b4ebc | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 | 2026-10-22 | 2026-10-21 |  | false |  |  |  |  | Team
-C0Kc5Jh7kWzxY9qKakYI8kAIf9m | Add OAuth, webhooks, sync and recovery after PP1 | nKY5vO1bg0u2XVpzDOmXsskAIDSz |  | Not started | Low | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 |  |  |  | false |  |  |  |  | C4 Platform-Email
NsSUAVg4VEChXYGsDLToDskAHv8Z | Optional: add tenant opt-in settings and API | nKY5vO1bg0u2XVpzDOmXsskAIDSz |  | Not started | Low | cc6f3715-42e2-48b1-80c1-1f8982decf2f | cc6f3715-42e2-48b1-80c1-1f8982decf2f | 2026-10-01 |  |  |  | false |  |  |  |  | C4 Platform-Email

## Buckets
Bucket ID | Bucket Name
nKY5vO1bg0u2XVpzDOmXsskAIDSz | Backlog
wHDew6aBm0qh2FuzAUEQAskAFS3E | Sprint 1
lvLKROICTE27IWeJgriNxckAMs2W | Sprint 2
XGKGyDgqAESDK8e2D43hN8kACEeA | Sprint 3
Mejb9NoRrkOXkOK0E9EoiskACnL9 | Sprint 4
FBkAtFWwAEmbTJ_6EVpCZckAKkTB | Sprint 5

## Users
User ID | User Name | Email
cc6f3715-42e2-48b1-80c1-1f8982decf2f | SAAYINATH K it23304338 | it23304338@my.sliit.lk
79aafd74-8432-4a9b-991d-08a7ef7b1a22 | JASINTHAN U it23154544 | it23154544@my.sliit.lk
11f012a9-8e1d-427d-bcf3-f252787021c2 | SRIRAMANA S it23136724 | it23136724@my.sliit.lk
d7043cfa-51ae-4438-9d08-62b6899b4ebc | SHATHURSINI.J it23164062 | it23164062@my.sliit.lk